## Deployment Checklist
Donor Registration & Donation Portal - Production Deployment Checklist
Section | Checklist Item | Status (✓/✗) | Remarks
Pre-Deployment - Apex | DonorController deployed & tested
Pre-Deployment - Apex | RazorpayRedirectController deployed & tested
Pre-Deployment - Apex | Test classes with 75%+ coverage
Pre-Deployment - Apex | All tests passing in production
Custom Object & Fields | Donation__c object deployed
Custom Object & Fields | All required fields deployed
Custom Object & Fields | Field-Level Security verified
Custom Object & Fields | Page Layout updated
External Integration Setup | Named Credential (Razorpay_API) created
External Integration Setup | Remote Site Setting added
External Integration Setup | Callback URL updated for production
Experience Cloud Setup | All pages set to Public access
Experience Cloud Setup | Flows added to respective pages
Experience Cloud Setup | Site published after deployment
Guest User Permissions | Lead - Read/Edit access
Guest User Permissions | Account - Read/Create access
Guest User Permissions | Contact - Read/Create access
Guest User Permissions | Donation__c - Read/Create access
Guest User Permissions | Apex class access granted
Post-Deployment Testing | Guest registration tested
Post-Deployment Testing | Lead conversion verified
Post-Deployment Testing | Donation record creation verified
Post-Deployment Testing | Razorpay payment link generated
Post-Deployment Testing | Successful payment updates status